## To-Do List
PROJECT: AI-Automated Planogram, RO Protol & RO Box
Target: 6 Minggu (10 Feb — 23 Mar 2026) │ Model: Design by Owner → Execution by Tim CI
ID | Task | Phase | Output | Owner | Effort | Start | Due | Status | Dependency | Notes
MINGGU 1-2: FOUNDATION (10-23 Feb)
F-01 | Import Master Artikel + Tier ke project | Foundation | - | Owner | 1d | 2026-02-10 | 2026-02-10 | To Do | - | Format: KODEMIX, Gender, Series, Article, Tier, Tipe
F-02 | Buat Master Store Database | Foundation | - | Owner | 1d | 2026-02-10 | 2026-02-10 | To Do | - | Kolom: Store_Name, Area, Max_Capacity
F-03 | Validasi & join sales data × master artikel | Foundation | - | Tim | 2d | 2026-02-11 | 2026-02-12 | To Do | F-01 | Identifikasi orphan codes
F-04 | Design format standar denah toko | Foundation | - | Owner | 2d | 2026-02-10 | 2026-02-11 | To Do | - | Format tabel, bisa dibaca mesin & manusia
F-05 | Isi denah 3-5 toko pilot | Foundation | - | SPV Area | 5d | 2026-02-12 | 2026-02-18 | To Do | F-04 | ⚠️ CRITICAL PATH — butuh turun ke toko
F-06 | Buat Google Form SPG Insight | Foundation | - | Owner | 1d | 2026-02-11 | 2026-02-11 | To Do | - | Opsional. Multiple choice, 5 menit isi
F-07 | Collect SPG insight toko pilot | Foundation | - | SPG | 3d | 2026-02-12 | 2026-02-14 | To Do | F-06 | Parallel dgn denah. Nice to have
F-08 | Script konsolidasi sales data | Foundation | - | Tim/Claude | 3d | 2026-02-12 | 2026-02-14 | To Do | F-01 | Gabung CSV → join master → adj avg → ranking
MINGGU 3: PLANOGRAM ENGINE (24 Feb - 2 Mar)
P-01 | Complete SKILL.md Section 2 (data processing) | Planogram | Planogram | Owner+Claude | 2d | 2026-02-24 | 2026-02-25 | To Do | F-03, F-08 | Step-by-step prosedur teknis
P-02 | Tambahkan worked example di SKILL.md | Planogram | Planogram | Owner+Claude | 1d | 2026-02-26 | 2026-02-26 | To Do | P-01 | 1 toko lengkap: raw data → final output
P-03 | Buat template output planogram (XLSX) | Planogram | Planogram | Tim | 2d | 2026-02-24 | 2026-02-25 | To Do | P-01 | 4 sheets: layout, storage, summary, comparison
P-04 | Test planogram toko pilot #1 | Planogram | Planogram | Owner+Claude+SPV | 2d | 2026-02-26 | 2026-02-27 | To Do | P-03, F-05 | Claude runs logic → SPV validasi
P-05 | Iterate & fix edge cases | Planogram | Planogram | Owner | 1d | 2026-02-28 | 2026-02-28 | To Do | P-04 | Update SKILL.md dari learnings
P-06 | Define target assortment output format | Planogram | Planogram→RO Protol | Owner | 0.5d | 2026-02-28 | 2026-02-28 | To Do | P-04 | Format: Store, Article, Display_Qty, Storage_Qty, Total
MINGGU 4: RO PROTOL ENGINE (3-9 Mar)
S-01 | Draft RO Protol SKILL.md | RO Protol | RO Protol | Owner+Claude | 2d | 2026-03-03 | 2026-03-04 | To Do | P-06 | Gap calc, source logic, constraints
S-02 | Define business rules mutasi | RO Protol | RO Protol | Owner+Ops | 1d | 2026-03-04 | 2026-03-04 | To Do | - | Min transfer, priority, approval flow
S-03 | Buat template output mutasi (XLSX) | RO Protol | RO Protol | Tim | 2d | 2026-03-05 | 2026-03-06 | To Do | S-01 | 4 sheets: summary, detail, whs depletion, timeline
S-04 | Test RO Protol data pilot | RO Protol | RO Protol | Owner+Claude+SPV | 2d | 2026-03-06 | 2026-03-07 | To Do | S-03, P-04 | Planogram output + current stock → mutasi rec
MINGGU 5: RO BOX ENGINE (10-16 Mar)
R-01 | Draft RO Box SKILL.md | RO Box | RO Box | Owner+Claude | 2d | 2026-03-10 | 2026-03-11 | To Do | S-01 | Weekly velocity, reorder point, constraints
R-02 | Integrasi dengan existing RO flow | RO Box | RO Box | Owner | 1d | 2026-03-11 | 2026-03-11 | To Do | - | AI draft → SPV review → existing flow
R-03 | Buat template output RO (XLSX) | RO Box | RO Box | Tim | 2d | 2026-03-12 | 2026-03-13 | To Do | R-01 | Kompatibel dgn existing RO input sheets
R-04 | Test RO pilot stores | RO Box | RO Box | Owner+Claude+SPV | 2d | 2026-03-13 | 2026-03-14 | To Do | R-03 | Simulate 1 minggu → SPV approve
MINGGU 6: INTEGRATION & ROLLOUT (17-23 Mar)
I-01 | End-to-end test full pipeline (1 toko) | Integration | All | Owner+Tim+SPV | 2d | 2026-03-17 | 2026-03-18 | To Do | R-04 | Sales → Planogram → RO Protol → RO Box
I-02 | Fix integration issues | Integration | All | Tim | 2d | 2026-03-18 | 2026-03-19 | To Do | I-01 | Format mismatch, edge cases
I-03 | Finalisasi semua SKILL.md | Integration | All | Owner | 1d | 2026-03-20 | 2026-03-20 | To Do | I-02 | Planogram + RO Protol + RO Box complete
I-04 | Buat SOP operasional ringkas | Integration | All | Owner | 1d | 2026-03-20 | 2026-03-20 | To Do | I-02 | Kapan run apa: quarterly/weekly/on-demand
I-05 | Training SPV & tim warehouse | Integration | All | Owner | 0.5d | 2026-03-21 | 2026-03-21 | To Do | I-03, I-04 | Demo end-to-end + Q&A
I-06 | Define rollout plan ke semua toko | Integration | All | Owner+Ops | 1d | 2026-03-21 | 2026-03-21 | To Do | I-05 | Phase 2: 1 area (Apr), Phase 3: all (Mei)

## Gantt Chart
GANTT CHART — 6 Week Timeline
Task | W1: Foundation | [6 empty] | W2: Foundation | [6 empty] | W3: Planogram | [6 empty] | W4: RO Protol | [6 empty] | W5: RO Box | [6 empty] | W6: Integration
| 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
FOUNDATION
F-01 Import Master Artikel
F-02 Master Store Database
F-04 Design format denah
F-06 Google Form SPG
F-03 Validasi sales × master
F-08 Script konsolidasi sales
F-05 ⚠️ Isi denah toko pilot
F-07 Collect SPG insight
PLANOGRAM ENGINE
P-01 SKILL.md Section 2
P-02 Worked example
P-03 Template output XLSX
P-04 Test pilot #1
P-05 Iterate & fix
P-06 Target assortment format
RO PROTOL ENGINE
S-01 RO Protol SKILL.md
S-02 Business rules mutasi
S-03 Template output mutasi
S-04 Test RO Protol pilot
RO BOX ENGINE
R-01 RO SKILL.md
R-02 Integrasi existing flow
R-03 Template output RO
R-04 Test RO pilot
INTEGRATION & ROLLOUT
I-01 E2E test full pipeline
I-02 Fix integration issues
I-03 Finalisasi SKILL.md
I-04 SOP operasional
I-05 Training SPV & WHS
I-06 Rollout plan

## Checkpoints
WEEKLY CHECKPOINTS
Minggu | Tanggal | Checkpoint | Pass Criteria | Status | Catatan
W1 | 16 Feb | Master data clean & joined | Sales + artikel + tier = 1 dataset, no orphans | To Do
W2 | 23 Feb | Denah 3 toko pilot ready | Format standar, data complete, validated | To Do
W3 | 2 Mar | Planogram pilot #1 done | Output reviewed & approved by SPV | To Do
W4 | 9 Mar | RO Protol pilot done | Mutasi list makes sense, validated by SPV | To Do
W5 | 16 Mar | RO Box pilot done | Weekly RO draft generated, SPV approved | To Do
W6 | 23 Mar | Full pipeline tested | End-to-end on 3 toko, all stakeholders sign off | To Do

## Risks & Dependencies
RISK REGISTER
Risk | Impact | Probability | Mitigation | Owner
Denah toko lambat dikumpulkan | 🔴 High | Tinggi | Mulai collect ASAP, prioritaskan pilot. Jangan tunggu semua toko. | SPV Area
Master artikel tidak clean / outdated | 🔴 High | Sedang | Validasi di minggu 1, identifikasi orphan codes. Jangan skip. | Owner
SPV tidak punya waktu validasi output | 🟡 Med | Sedang | Schedule dedicated 1-2 jam review slots per minggu. | Owner
Edge cases tidak tertangkap saat pilot | 🟡 Med | Tinggi | Iterative testing, flag system di setiap output. Expect iteration. | Owner+Tim
Format output tidak kompatibel antar engine | 🟡 Med | Rendah | Define output format di awal setiap phase. Test integration early. | Owner
Scope creep: request tambahan dari stakeholder | 🟢 Low | Tinggi | Stick to pilot scope. Log requests untuk phase 2. | Owner
DEPENDENCY FLOW
From |  | To | Keterangan
Foundation Layer | → | ALL engines | Master data + templates harus selesai sebelum engine apapun jalan
Planogram output | → | RO Protol input | Target assortment per toko = basis gap calculation RO Protol
RO Protol output | → | RO baseline | Stock setelah redistribusi = starting point RO Box weekly
Denah toko (F-05) | → | Planogram test (P-04) | ⚠️ CRITICAL: tanpa denah, tidak bisa test planogram
Master Artikel (F-01) | → | Script sales (F-08) | Join sales data butuh master untuk gender, series, tier

## Current State
CURRENT STATE — per 10 Feb 2026
Komponen | Status | Lokasi / Keterangan | Action Needed
Sales data 2025 (Jan-Sep) | ✅ Ready | Project files (CSV, 9 files) | -
Sales data 2024 (YTD) | ✅ Ready | Project files (XLSX) | -
Master Artikel + Tier | ✅ Ready | Ada di sistem (belum di project) | Upload ke project
Store capacity database | ✅ Partial | Ada di inventory skill | Consolidate ke 1 file
Planogram SKILL.md Sec 1 | ✅ Ready | Uploaded v1.0 | -
Planogram SKILL.md Sec 2 | ❌ Belum | Placeholder | Isi bareng Claude
Denah toko template | ❌ Belum | - | Design format + isi pilot stores
SPG Insight template | ❌ Belum | - | Buat Google Form (opsional)
RO Protol SKILL.md | ❌ Belum | - | Draft di minggu 4
RO Box SKILL.md | ❌ Belum | Ada doc RO tapi konteks beda | Draft di minggu 5